## Slide 1
INSTITUTE OF PROJECT MANAGEMENT
IPM Hub Mobile App
Project Status & Progress Overview
June 2026
12+
Screens Built
5
Major Modules
React Native
0.74.5
Tech Stack

## Slide 2
PROJECT OVERVIEW
What We're Building
A native mobile app (iOS & Android) for the Institute of Project Management community.
Built with React Native 0.74.5 + TypeScript, connecting to a WordPress / BuddyBoss / LearnDash / WooCommerce backend at hub.instituteprojectmanagement.com.
The app unifies social features, professional learning, events, mentorship, and a gamified badge system in a single branded experience.
Frontend
React Native 0.74.5, TypeScript
Backend
WordPress + BuddyBoss + LearnDash + WooCommerce
Auth
JWT (Keychain), Google Sign-In, LinkedIn OAuth
Design
Figma (pixel-perfect), Runda font, IPM palette
Dev Env
Android Studio, Windows/PowerShell, D:\IPMMobileApp

## Slide 3
COMPLETED SCREENS & FEATURES
Onboarding & Auth
Splash Screen
Sign Up
Sign In
Email Verification
Welcome Screen
Profile Setup
✓
Social & Community
Feed
Forums (73 taxonomy tags, 5 filter categories)
Introductions
Mentors Directory
Resources
✓
Profile & Settings
Member Profile (5 tabs)
Edit Profile (6 screens)
Account Settings
✓
Learning & Events
Courses Screen
Course Detail Screen
Lesson Detail Screen
Certifications
Events Screen
Event Detail
Event Thank You
✓
Messaging & Store
DM List
DM Conversation
New Message
DM Members
Store (Courses / Certs / PM Softwares tabs)
✓
Badges (Phase 1 UI)
Badges Screen — IPM Member Badge
Gamified badge display
Badge progress UI (awaiting live endpoint)
✓

## Slide 4
KEY TECHNICAL ACHIEVEMENTS
🔐 Secure Authentication
JWT stored in device Keychain; first-login detection via server-side BuddyBoss xProfile check (Job Title field empty = new user)
📡 Custom API Layer
mu-plugin ipm-register.php with WPCode integration; all real BuddyBoss/LearnDash/WooCommerce endpoints wired — no fake data policy
🎨 Pixel-Perfect UI
Figma specs treated as exact requirements; Runda font family, IPM brand palette (Navy #192546, Light Blue #46B0E3); 73 real forum taxonomy tags
💬 Full Direct Messaging
BuddyBoss /messages API integration with thread support, recipients array handling, and new-conversation flow
🛡️ Android Compatibility
Fixed: no atob() on Hermes, overflow:hidden causing zero-height cards, gap→marginBottom, nested TouchableOpacity tap issues resolved with onStartShouldSetResponder
🎓 Courses & Learning
LearnDash course/lesson screens with progress tracking; Certifications module; Store with Courses, Certifications, and PM Software tabs

## Slide 5
ACTIVE TASKS IN PROGRESS
In Progress
Third-Party Integrations (APIs)
Due: Tomorrow
Google Sign-In (awaiting correct webClientId from backend), LinkedIn OAuth via WebView modal, and ensuring all third-party API connections are production-ready.
Overdue
IPM HUB Store
Due: 6/22/26
Store screen built with Courses, Certifications, and PM Softwares tabs. Real product pricing/descriptions need to be exposed via custom backend endpoints (ACF fields not yet in REST API).
Overdue
Badge Gamification (IPM Member Badge)
Due: 3 days ago
UI for IPM Member Badge complete. Awaiting GET /ipm/v1/badge-progress backend endpoint — full API spec has been produced. Once live, badge points and profile drawer will be updated.
Overdue
Full Badges System (Other Badges)
Due: 3 days ago
Phase 2 gamified badge system encompassing all badge types beyond IPM Member Badge. Dependent on badge-progress endpoint and backend badge logic being finalized.

## Slide 6
PENDING BACKEND WORK
1
Badge Progress Endpoint
GET /ipm/v1/badge-progress does not yet exist. Full API specification has been documented and is ready for implementation. Required before Badges screen can display live data.
2
Google Sign-In OAuth Client
The Web Application-type OAuth Client ID (webClientId) is still needed. The current Android-type client ID cannot fulfill this role. Once provided, Google Sign-In will be fully operational.
3
LinkedIn Sign-In Backend
POST /ipm/v1/linkedin-token endpoint has not yet been built. The frontend LinkedIn WebView OAuth modal is ready and waiting for this backend piece.
4
Store Product Data (ACF Fields)
Real product pricing, descriptions, and metadata are likely in Advanced Custom Fields not currently exposed by REST endpoints. Custom endpoints or ACF exposure needed for the Store to display live data.
5
LearnDash REST Permissions
/ldlms/v1/sfwd-courses returns 401 learndash_rest_forbidden. Permissions need to be resolved on the backend to enable the Courses module to pull live data.

## Slide 7
WHAT'S AHEAD
Near-Term
Wire Badges screen to live badge-progress endpoint once built
Profile drawer badge point update
Forum Topic Detail view (not yet built)
Notifications screen
iOS build strategy (via backend colleague's Mac, EAS Build, or GitHub Actions macOS runners)
Phase 2
PDU Tracker
Checkout & Payment flow
Full Badges System — all badge types beyond IPM Member
Apple Developer Program enrollment ($99/yr) for device testing
Production release preparation

## Slide 8
Building Something
Meaningful
The IPM Hub Mobile App brings together community, learning, events, and professional growth — all in one native experience for project management professionals.
hub.instituteprojectmanagement.com